## Slide 1: FDOT District 5 Construction Special Projects
Local Agency Program
Construction Phase Overview

## Slide 2: What is LAP?
LAP is the Local Agency Program.
LAP is the mechanism used by the Federal Highway Administration(FHWA) to fund Local Agency administered transportation related projects.
FHWA has tasked FDOT with stewardship of these federal funds. Our role as Construction Special Projects is to help you achieve a successful construction phase of your project while meeting all of the requirements of the program.

## Slide 3: Why are we here today?
The main objective of this training is to empower you as the owner of your LAP project. This program comes with many requirements you will be expected to meet. We are here to help guide you through them.
Your Agency’s performance may impact future availability of LAP funds, so cooperation and adherence to LAP obligations during the construction phase are key to successful projects now and in the future.
  LAP Performance Evaluations are completed for all phases of a LAP project and are a factor in determining funding for additional projects.
A successful LAP project will pass any District, State, or Federal audit, another benefit of proper Local Agency administration.

## Slide 4: LAP Performance Evaluation
Performance evaluations are completed using the Local Agency Program Performance Evaluation Form No. 525-010-50. The Department provides the evaluation to the Local Agency as soon as practicable and no more than 30 days after final acceptance and/or the processing of the final project close out package by the Department (see LAP Agreement, Section 13). The performance evaluation cannot be completed in full until a final invoice for the project has been accepted and processed by the Department. (LAP Manual – Chapter 2)
Simple Grading Criteria:
  1 – Unsatisfactory Performance
  2 – Satisfactory Performance
  3 – Above Satisfactory Performance
Most aspects of your project are evaluated, so adherence to LAP requirements and guidelines is highly recommended to help you attain the best possible ratings.
  Ratings may affect future LAP Certification and/or funding, so 3s are your target!

## Slide 5: The LAP Manual
The LAP Manual is the main governing document for all LAP projects. It is a constantly evolving publication that covers all facets of the Program, from funding allocation to project closeout.
LAP Manual 1.5.1:
  “The Department is empowered by legislative authority to contract with other Local Agencies to plan, develop, design, acquire right of way, and construct transportation facilities. The Department reimburses these Local Agencies for services provided to the public.”

## Slide 6: Don’t Confuse Your Contracts
LAP Agreement
Agreement between the FDOT (Department)and the local government (Agency).
Identifies responsibilities of the Department and the Agency, project scope, funding amounts, brief project schedule, ineligible costs, etc.
May be modified via Supplemental Agreement between the Agency and the Department.
Construction Contract
Agreement between the Agency and their Contractor.
Identifies expectations of the contractor, project scope, awarded amounts, contract time, etc.
May be modified via change order between the Agency and the Contractor.

## Slide 7: On the Way to Construction
While this training focuses on the Construction phase, your Agency will be dealing with other FDOT groups before you are ready to advertise:
Local Programs Group
LAP Design Group
Construction Special Projects

## Slide 8: On the Way to Construction
The Local Programs Group will work with your Agency to establish project scope, schedule and funding levels, and prepare the LAP Agreement and any subsequent Supplemental Agreements.
The Design Group will review your:
  Construction Documents (plans, specifications package, and bid documents) to make sure they are consistent with LAP requirements.
  Consultant CEI staffing and fees/Agency CEI staffing to confirm adequate oversight is in place.
Once your construction documents are finalized, the Design Group will pass your project off to our group, Construction Special Projects.

## Slide 9: Welcome to Construction
The passing of your construction documents from Design to Construction will trigger the Local Programs Group to execute your LAP Agreement and issue your Notice to Proceed (NTP) authorizing you to advertise the construction phase of your project.
    Any costs incurred under this Agreement before the Agency has received a written NTP from the Department will not be reimbursable. (LAP Manual Chapter 5 and LAP Agreement)
Once your NTP to advertise is sent, you will receive a “Welcome to Construction” email from our group (D5-ConstructionSpecialProjects@dot.state.fl.us) letting you know your project is officially in the Construction Phase. We will be your primary point of contact during through project closeout.

## Slide 10: Construction Special Projects Staff
Vince Vacchiano
Construction Manager
Rick Grooms
Special Projects Construction
Ashley Henning
Contract Support Specialist
Deborah White
Consultant Project Administrator
Chris Jones
Consultant Quality Assurance Specialist

## Slide 11: Special Projects Construction Core Functions
  During Procurement
    Review Addenda and Bid Tabulations/Bid Analysis and provide concurrence prior to publication of addenda and contract award.
  During Construction
    Project Tracking/Records - Track project milestones and review GAP to ensure Agency is keeping it up to date.
    Review contract changes (change orders) before providing concurrence.
    Oversight and Monitoring - Coordinate and attend preconstruction meetings, Quality Assurance Reviews and field visits.
    Process invoices and project close out documents.

## Slide 12: Procurement - Advertisement
  Your project must be advertised in a newspaper of general circulation in the County where the project is located. All LAP projects must have two advertisements within a minimum of three weeks. (LAP Manual Chapter 21)
    When a pre-qualified contractor is not required and estimate exceeds $500,000, at least one of the two ads must appear in a newspaper a minimum of 30 days prior to bid opening.
    When a pre-qualified contractor is required, both ads must appear in a newspaper at least three weeks prior to bid opening.
  A copy of the Newspaper Advertisement, showing the broadcast dates, must be uploaded into GAP.
  It is imperative that we have a copy of the same documents that you advertise to the public.

## Slide 13: Procurement - Addenda
All addenda (changes made after the project is advertised, but before bids are opened) must be concurred with by the Department prior to issuance to bidders.(LAP Manual Chapter 21)
  Identify in an email any changes being proposed and provide any attachments/plan revisions/backup documentation listed on your addenda for review.
  Review Davis-Bacon wage rates 10 days prior to the bid opening date to ensure most recent wage rates are included in the construction contract (LAP Manual Chapters 6 and 21).
    Issue an addendum updating the wage rates if there has been a new version published. If you have to change it after the contract is awarded (via change order), contractor may want to be compensated.

## Slide 14: Procurement – Bid Opening and Award
Bids must be publicly opened and read aloud. (LAP Manual Chapter 21)
  If any individual bids are rejected for any reason, the Local Agency must provide justification to the Department.
  Specific bid concurrence request instructions are available and will also be sent to you upon scheduled bid opening date.
  Certified bid tabulation will be key in your request to award your project to the lowest responsive and responsible bidder (signed by Local Agency staff).
  Agency will need to identify any funding shortage and be prepared to cover the difference with Agency funds.
  Agency will need to justify deviations for any bid items whose prices differ from the Engineer’s Estimate by more than 10%, high or low. This needs to be done for the apparent low responsive/responsible bidder only.

## Slide 15: Bid Tabulation
FDOT PAY ITEM | ITEM | UNIT | QUANTITY | EOPC UNIT PRICE | EOPC AMOUNT | Contractor 1 | Contractor 1 | Contractor 2 | Contractor 2 | Contractor 3 | Contractor 3
101-1 | MOBILIZATION | LS | 1 | $49,790.15 | $49,790.15 | $67,257.37 | $67,257.37 | $76,000.00 | $76,000.00 | $63,440.85 | $63,440.85
102-1 | MAINTENANCE OF TRAFFIC | LS | 1 | $38,053.90 | $38,053.90 | $47,531.70 | $47,531.70 | $85,000.00 | $85,000.00 | $88,476.85 | $88,476.85
104-1 | ARTIFICIAL COVERINGS/ROLLED EROSION CONTROL PRODUCTS | SY | 122 | $2.00 | $244.00 | $6.57 | $801.54 | $6.00 | $732.00 | $18.82 | $2,296.04
104-10-3 | SEDIMENT BARRIER | LF | 22,776 | $1.60 | $36,441.60 | $0.67 | $15,259.92 | $1.50 | $34,164.00 | $1.41 | $32,114.16
104-15 | SOIL TRACKING PREVENTION DEVICE | EA | 2 | $2,790.00 | $5,580.00 | $1,789.19 | $3,578.38 | $1,500.00 | $3,000.00 | $1,577.00 | $3,154.00
104-18 | INLET PROTECTION SYSTEM | EA | 2 | $111.00 | $222.00 | $78.31 | $156.62 | $120.00 | $240.00 | $504.78 | $1,009.56
107-1 | LITTER REMOVAL AND DISPOSAL | AC | 78.84 | $40.00 | $3,153.60 | $132.02 | $10,408.46 | $60.00 | $4,730.40 | $327.56 | $25,824.83
107-2 | MOWING | AC | 67.36 | $50.00 | $3,368.00 | $82.68 | $5,569.32 | $60.00 | $4,041.60 | $247.50 | $16,671.60
110-1-1 | CLEARING AND GRUBBING (5.21 AC) | LS | 1 | $62,520.00 | $62,520.00 | $47,484.48 | $47,484.48 | $43,000.00 | $43,000.00 | $27,193.45 | $27,193.45
110-7-1 | MAILBOX, F&I, SINGLE | EA | 8 | $150.00 | $1,200.00 | $228.52 | $1,828.16 | $180.00 | $1,440.00 | $225.00 | $1,800.00
120-1 | REGULAR EXCAVATION | CY | 2,536 | $6.00 | $15,214.20 | $27.06 | $68,624.16 | $29.00 | $73,544.00 | $16.62 | $42,148.32
120-6 | EMBANKMENT | CY | 1,041 | $10.00 | $10,412.00 | $21.83 | $22,725.03 | $21.45 | $22,329.45 | $87.86 | $91,462.26
160-4 | TYPE B STABILIZATION | SY | 17,665 | $4.25 | $75,076.25 | $6.57 | $116,059.05 | $4.35 | $76,842.75 | $7.00 | $123,655.00
285-701 | OPTIONAL BASE, BASE GROUP 01 | SY | 14,472 | $15.00 | $217,080.00 | $8.64 | $125,038.08 | $8.55 | $123,735.60 | $8.00 | $115,776.00
286-1 | TURNOUT CONSTRUCTION | SY | 368 | $18.00 | $6,624.00 | $22.75 | $8,372.00 | $11.40 | $4,195.20 | $53.44 | $19,665.92
334-1-53 | SUPERPAVE ASPHALTIC CONC, TRAFFIC C, PG 76-22 | TN | 12 | $105.00 | $1,260.00 | $273.15 | $3,277.80 | $160.00 | $1,920.00 | $226.60 | $2,719.20
337-7-82 | ASPHALT FRICTION COURSE, TRAFFIC C, FC-9.5, PG 76-22 | TN | 728.5 | $125.00 | $91,062.50 | $127.05 | $92,555.93 | $150.00 | $109,275.00 | $117.45 | $85,562.33
339-1 | MISCELLANEOUS ASPHALT PAVEMENT | TN | 79.8 | $175.00 | $13,965.00 | $86.06 | $6,867.59 | $150.00 | $11,970.00 | $227.00 | $18,114.60
522-2 | CONCRETE SIDEWALK AND DRIVEWAYS, 6" THICK | SY | 45 | $48.50 | $2,182.50 | $71.10 | $3,199.50 | $82.00 | $3,690.00 | $74.80 | $3,366.00

## Slide 16: Bid Tab with Deviations Explained
FDOT PAY ITEM | ITEM | UNIT | QTY | CON 1 | CON 1 | EOPC UNIT PRICE | EOPC AMOUNT | Del EOPC | % | Analysis of Differences
101-1 | MOBILIZATION | LS | 1 | $67,257.37 | $67,257.37 | $49,790.15 | $49,790.15 | $17,467.22 | 35.1 | CON 1 office is in Lecanto on the other side of Inverness in Citrus County. Balances w/Clearing and Grubbing. And Project is only fifty (50) days so it cannot be front end loaded.
102-1 | MAINTENANCE OF TRAFFIC | LS | 1 | $47,531.70 | $47,531.70 | $38,053.90 | $38,053.90 | $9,477.80 | 24.9 | Longer commute for set up, daily, and nightly checks due to CON 1’s office in Lecanto. Traffic Construction Control is the responsibility of contractor and Project is only fifty (50) days so it cannot be front end loaded.
104-1 | ARTIFICIAL COVERINGS/ROLLED EROSION CONTROL PRODUCTS | SY | 122 | $6.57 | $801.54 | $2.00 | $244.00 | $557.54 | 228.5 | It is not cost effective for CON 1 to reuse artificial coverings. Delta less than 0.5% on Total.
104-10-3 | SEDIMENT BARRIER | LF | 22,776 | $0.67 | $15,259.92 | $1.60 | $36,441.60 | -$21,181.68 | -58.1 | CON 1 reuses barrier. Final fees should not be impacted with Lower unit cost and large quantity.
104-15 | SOIL TRACKING PREVENTION DEVICE | EA | 2 | $1,789.19 | $3,578.38 | $2,790.00 | $5,580.00 | -$2,001.62 | -35.9 | CON 1's field built BMP uses local materials . Delta less than 0.5% on Total.
104-18 | INLET PROTECTION SYSTEM | EA | 2 | $78.31 | $156.62 | $111.00 | $222.00 | -$65.38 | -29.5 | Delta less than 0.5% on Total. CON 1 left $65 on the table.
107-1 | LITTER REMOVAL AND DISPOSAL | AC | 78.84 | $132.02 | $10,408.46 | $40.00 | $3,153.60 | $7,254.86 | 230.1 | Litter of adjacent I-75 is included in CON 1's bid. Similar Items 4,8,9,12, & 13 balance out.
107-2 | MOWING | AC | 67.36 | $82.68 | $5,569.32 | $50.00 | $3,368.00 | $2,201.32 | 65.4 | Litter removal of adjacent I-75 is included in CON 1's mowing bid. Similar Items 4,8,9,12, & 13 balance out. Delta less than 0.5% on Total.
110-1-1 | CLEARING AND GRUBBING (5.21 AC) | LS | 1 | $47,484.48 | $47,484.48 | $62,520.00 | $62,520.00 | -$15,035.52 | -24.0 | CON 1 will store equipment on site, saving hauling time and completing activity quicker. Similar Items 5,8,9,12, & 13 balance out. Therefore okay
110-7-1 | MAILBOX, F&I, SINGLE | EA | 8 | $228.52 | $1,828.16 | $150.00 | $1,200.00 | $628.16 | 52.3 | Mailboxes have to withstand summer vacation construction time. Delta less than 0.5% on Total.
120-1 | REGULAR EXCAVATION | CY | 2,536 | $27.06 | $68,624.16 | $6.00 | $15,214.20 | $53,409.96 | 351.1 | CON 1 maintains a fleet of Heavy Equipment and Vehicles based at our Lecanto Florida location. Highs and low of Items 15-19 Balance out
120-6 | EMBANKMENT | CY | 1,041 | $21.83 | $22,725.03 | $10.00 | $10,412.00 | $12,313.03 | 118.3 | CON 1 maintains a fleet of Heavy Equipment and Vehicles based at our Lecanto Florida location. Highs and low of Items 15-19 Balance out
160-4 | TYPE B STABILIZATION | SY | 17,665 | $6.57 | $116,059.05 | $4.25 | $75,076.25 | $40,982.80 | 54.6 | CON 1 employees are skilled for the many phases of work we provide. Highs and low of Items 15-19 Balance out
285-701 | OPTIONAL BASE, BASE GROUP 01 | SY | 14,472 | $8.64 | $125,038.08 | $15.00 | $217,080.00 | -$92,041.92 | -42.4 | CON 1 maintains Means and Methods for FDOT Standards for quality workmanship. Highs and low of Items 15-19 Balance out
286-1 | TURNOUT CONSTRUCTION | SY | 368 | $22.75 | $8,372.00 | $18.00 | $6,624.00 | $1,748.00 | 26.4 | CON 1 fee is based on Sumter County driveways. Delta less than 0.5% on Total.
334-1-53 | SUPERPAVE ASPHALTIC CONC, TRAFFIC C, PG 76-22 | TN | 12 | $273.15 | $3,277.80 | $105.00 | $1,260.00 | $2,017.80 | 160.1 | Twelve (12) tons of asphalt is too small a quantity to obtain volume discount. Asphalt items, 20,21,22 Balance out. Delta less than 0.5% on Total.
337-7-82 | ASPHALT FRICTION COURSE, TRAFFIC C, FC-9.5, PG 76-22 | TN | 728.5 | $127.05 | $92,555.93 | $125.00 | $91,062.50 | $1,493.43 | 1.6 | Asphalt items, 20,21,22 Balance out. Delta less than 0.5% on Total.
339-1 | MISCELLANEOUS ASPHALT PAVEMENT | TN | 79.8 | $86.06 | $6,867.59 | $175.00 | $13,965.00 | -$7,097.41 | -50.8 | CON 1 Controls yield, compaction, and their on-grade paving begins prior to the first equipment arriving on site. Asphalt items, 20,21,22 Balance out.
522-2 | CONCRETE SIDEWALK AND DRIVEWAYS, 6" THICK | SY | 45 | $71.10 | $3,199.50 | $48.50 | $2,182.50 | $1,017.00 | 46.6 | Concrete plant is further away from this job site. Delta less than 0.5% on Total

## Slide 17: Procurement – Bid Opening and Award
Options for Agency upon bid opening:
  Award to lowest responsive and responsible bidder.
      Justification required for deeming a bidder non-responsive/responsible
  Reject all bids and rebid the project. Possible reasons for rejecting bids:
      Low bidder significantly exceeds engineer’s estimate
      Unbalanced unit prices
      Lack of Competition - Less than 3 bids received
  Reduce scope – requires justification.
      Must not alter the bidding result - will likely require re-advertisement.
All of these options require Department concurrence before proceeding.

## Slide 18: Project Administration/Records - GAP
Local Agency Program Information Tool (GAP) is a central location for electronic project files.
  The use of GAP is required on all LAP projects (LAP Manual Chapter 2 and LAP Agreement)
  During the Construction phase, you should begin using GAP as soon as the project is advertised.
  FDOT, FHWA, and the Local Agency can access GAP to facilitate audits and review all project information as needed.
    Contains relevant agency information
      LAP Certification/Responsible Charge/Agency GAP Administrator
    Contains project information for all LAP projects produced after 2011.
      Procurement information
      Contract and contract changes

## Slide 19: Oversight and Monitoring Pre-Construction Meeting
Once the project is awarded, your Agency will need to hold a pre-construction meeting with all pertinent stakeholders associated with the project. (LAP Manual Chapter 23).
  Agency
  Contractor
  EOR
  Subcontractors
  Construction Special Projects Group
  Consultant CEI team
  Utilities
  Emergency Services
  Other interested parties

## Slide 20: Oversight and Monitoring Pre-Construction Meeting
Agency to prepare Pre-Construction Meeting Agenda and provide to Construction Special Projects for review at least 7 days in advance of the meeting. Some of the key issues that need to be covered are:
  Project Scope and Description
  Contract Specifications
  Contract Duration and Value
  Contract Compliance – Many times this is a separate meeting close or adjacent to pre-con.
  NTP Date
  Roles and Responsibilities
  Contact Information – all parties
  Notable Traffic Control Issues
  Utility Work
  Emergency Plan

## Slide 21: Oversight and Monitoring Agency Construction Administration
As the owner of the project, your agency will be responsible for all aspects of Construction (LAP Manual Chapter 23) which include:
  Project inspection
  Project administration and recordkeeping
  Materials acceptance testing and verification
  Federal contract compliance
  Proper invoicing and closeout
Enlisting a CCEI firm is encouraged, and many times funded in your agreement, but as the owner, your agency is ultimately responsible for all project issues.

## Slide 22: Oversight and Monitoring Quality Assurance Reviews and Field Visits
Examples of Agency Project Activities that will be checked during QARs:
  Daily Work Reports/Inspection Records for every day of contract time and current field books
  Current CPM Schedule
  Compliant bulletin board in place
  MOT plan is current and implemented correctly – this includes pedestrian MOT
  ADA Compliance
  Materials testing records and certifications
  Buy America Certification, as applicable
  Proper use of MAC (Materials Acceptance and Certification), as applicable

## Slide 23: Oversight and Monitoring Quality Assurance Reviews and Field Visits
Our QA staff will visit your project to perform periodic Quality Assurance Reviews (QARs).
  Will be scheduled with the agency representative responsible charge for construction.
  Can cover everything from safety and constructability issues in the field to records verification in your project files.
  Following an independent review of agency’s project documentation, an exit interview to discuss findings will be held with agency PM.
Agency will receive completed QAR form within 3 business days of the review, advising of any deficiencies and requesting an appropriate Corrective Action Plan.
  Any issues compromising safety will be addressed immediately.
Random field visits are performed as well, Agency attendance is not required.

## Slide 24: Oversight and Monitoring – Contract Changes
Refers to changes in the contract between the Agency and the contractor.
Written concurrence from FDOT is required for all contract changes before they are executed with the contractor.
Minor changes to existing pay item quantities may not require a contract change and may be documented on overrun/underrun spreadsheet at project closeout.
  This will depend on your construction contract.
  Please consult District Construction staff for guidance on this before instituting change.

## Slide 25: Oversight and Monitoring – Contract Changes
Contract Changes must be accompanied by backup justification.
  This justification will contain several important details, among them are:
    Reason for change, and recommendation by Agency on how to proceed.
    Agency determination of federal-aid eligibility/ineligibility of added time and/or costs
    Entitlement Analysis (Construction Project Administration Manual (CPAM) Guidance Document 7-3-A)
    Time Analysis and updated CPM schedule if applicable
    Engineer’s Estimate of changes to costs
      Include historical cost averages for new pay items
    Plan revisions or other applicable modifying documents

## Slide 26: Oversight and Monitoring – Invoicing
Invoicing to be submitted electronically at least quarterly. LAP Agreement will specify timeline.
    Completed LAP Invoice Transmittal with charges broken down by phase (58/68)
    Local Programs Project Monitoring Status Report (PMSR) to accompany invoices
    Agency summary sheet of reimbursement being requested
      Should be cumulative and list all costs to date, regardless of eligibility, including past invoices.
        LAP vs. Local Agency Funding percentage or applicable match
        Federal-Aid eligible/ineligible costs
      Contractor Pay Application
      Required Certifications
      Proof of payment from Agency to contractor
      For CEI Costs, if percentage of reimbursement differs from construction costs, this will need to be billed on a separate Invoice Transmittal – PMSR should be specific to phase being billed
        Signed time sheets for Consultant CEI personnel or Agency CEI staff – if applicable

## Slide 27: Oversight and Monitoring – Closeout
THE FINAL CLOSEOUT PACKAGE MUST CONTAIN:
Invoice Transmittal Sheet - completed and signed by Agency P.E.
Contractor's pay application - signed off by Agency PM
Completed Compliance Checklist
Proof of payment from Agency to Contractor
Overrun/Underrun Spreadsheet of existing pay items
Substantial and/or Final Completion Notice from bid documents - completed and signed (these are the letters that will be uploaded into GAP)
Lien Releases or Consent of Surety from Prime to Agency
Agency Certification Letter
As-Built Plans
Materials Certification
Record of Final plans and Documents
Federal Project Closeout Form

## Slide 28: Questions and Contact Information
Agreement/funding related issues/Invoices for non-LAP Projects:
  D5-LocalPrograms@dot.state.fl.us
Design/Bid Documents/CEI Issues (before project is passed to Construction) should be directed to your specific FDOT Design PM
All Construction Issues including LAP Construction and CEI Invoices:
  D5-ConstructionSpecialProjects@dot.state.fl.us

## Slide 29: Questions? and Contact Information
We covered a wide range of topics today, are there any remaining questions?
While our group email address is the best way to get to all of us, we all have phones as well.
  Most of us are currently teleworking, so email is your best way to contact us.
Feel free to call us about any of your LAP construction issues. We ask that calls come from your agency, not from your CCEI firm or other non-agency representative.
Vince Vacchiano 386-943-5406
Rick Grooms 386-943-5364
Ashley Henning 386-943-5463
Deborah White 386-943-5396
Chris Jones 386-943-5385
And of course: D5-ConstructionSpecialProjects@dot.state.fl.us

## Slide 30: Thank you for your time……………
We hope that this training was informative and helpful.
We want your project to result in a quality product that is safe, on time, and on budget, allowing your agency to maximize available funding.
Please direct all questions about the construction phase of your LAP project to:
D5-ConstructionSpecialProjects@dot.state.fl.us
We no longer have a dedicated website, but we prepared a list of hyperlinks that you may find to be very useful:
  D5 Special Projects Guide
Thanks!