## Example
CEI CONSULTANT ESTIMATED STAFFING
FPN: ######-#-68-01
Project Description | 2014 | [13 empty] | 2015
SR 1 Paved Shoulder project from Main St to 1st St | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Man Months | Man Hours | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Man Months | Man Hours | Total Project Hours
PERSONNEL CLASSIFICATION
CEI Senior Project Engineer | 2014 Nov: 0.05; 2014 Dec: 0.05 | 0.1 | 16.5 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | [6 empty] | 0.3 | 49.5 | 66
CEI Project Administrator | 2014 Nov: 0.2; 2014 Dec: 0.25 | 0.45 | 74.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [6 empty] | 1.5 | 247.5 | 321.75
CEI Contract Support Specialist | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
CEI Senior Inspector | 2014 Nov: 0.5; 2014 Dec: 1 | 1.5 | 247.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | [6 empty] | 5.5 | 907.5 | 1155
CEI Inspector/Intern | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
CEI Inspector/Intern | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
CEI Asphalt Plant Inspector | 2014 Nov: 0; 2014 Dec: 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | [6 empty] | 0.5 | 82.5 | 82.5
RCS | 2014 Nov: 0.2; 2014 Dec: 0.2 | 0.4 | 66 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | [6 empty] | 1.4 | 231 | 297
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 2.45 | 404.25 | [12 empty] | 9.2 | 1518 | 1922.25
Instructions:
1) Identify the personnel that will be required on the project. Place the required positions in "Personnel Classification column"
2) Once all staff has been identified, place the percentage of time that you anticipate they will serve on the job. For example, if the CEI Senior Project Engineer will only be needed on the job 20% of time during a month, place a .20 in each month they will be required on the job. Complete this process for all required staff.
3) Based on the percentages entered, this will create a total man hour estimate for that position.
4) Look at the "Total Project Hours" column to determine the number of man hours that will be required for each position and the entire project.
Please Note: Based on 165 hours in a month (1 man month equals 165 hours)

## CEI Blank Form
DESIGN CONSULTANT ESTIMATED STAFFING
FPN: ######-#-38-01
Project Description | 2014 | [13 empty] | 2015
SR 1 Paved Shoulder project from Smith Street to Lemon Avenue | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Man Months | Man Hours | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Man Months | Man Hours | Total Project Hours
PERSONNEL CLASSIFICATION
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
[13 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0
Please Note: Based on 165 hours in a month (1 man month equals 165 hours)